## Slide 1
Project Plan
1/3
1 ideation sprint
6 production sprints
  3 stages + 1 polish sprint
Weekly sprints with retrospectives at the end
  Sprints end before milestone deadlines
Documentation until June 9th

## Slide 2
April, 2020
2/3
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
 |  | 1 | 2 | 3 | 4 | 5
6 | 7 | 8 | 9 | 10 | 11 | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
20 | 21 | 22 | 23 | 24 | 25 | 26
27 | 28 | 29 | 30 |  |  | 
22:00 First Pitch Presentation
10:00-16:00 Mandatory
Mentoring
22:00 Intermediate Presentation
10:00
Watch Presentations
Kick-off Presentation
R
R
R
R
QA
R
External deadlines
Mentoring
Sprints
Retrospectives
QA
Playtesting
QA

## Slide 3
May, 2020
3/3
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
 |  |  |  | 1 | 2 | 3
4 | 5 | 6 | 7 | 8 | 9 | 10
11 | 12 | 13 | 14 | 15 | 16 | 17
18 | 19 | 20 | 21 | 22 | 23 | 24
25 | 26 | 27 | 28 | 29 | 30 | 31
10:00-16:00 Mandatory
Mentoring
22:00 Final
Presentations
9:45-13:00 Watch Presentations
R
R
R
R
External deadlines
Mentoring
Sprints
Retrospectives
QA
Playtesting

## Slide 4
April, 2020
1/2
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
 |  | 1 | 2 | 3 | 4 | 5
6 | 7 | 8 | 9 | 10 | 11 | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
20 | 21 | 22 | 23 | 24 | 25 | 26
27 | 28 | 29 | 30 |  |  | 
Stage 1
Stage 2
Stage 3

## Slide 5
May, 2020
2/2
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
 |  |  |  | 1 | 2 | 3
4 | 5 | 6 | 7 | 8 | 9 | 10
11 | 12 | 13 | 14 | 15 | 16 | 17
18 | 19 | 20 | 21 | 22 | 23 | 24
25 | 26 | 27 | 28 | 29 | 30 | 31
Stage 3
Polish